PROJECT MANAGEMENT AND IMPLEMENTATION TIMETABLE

"This project has been funded with support from the European Commission. This communication reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein"

| LAWGEM DURATION – Oct 2019 – August 2022 | ACTIVITIES | COORDINATOR`S RESPONSIBILITY | PARTNER COUNTRIES COORDINATORS` RESPONSIBILITY |
| --- | --- | --- | --- |
| October 2019 | -Intensive communication between members of the Consortium. -Preparation of the partnership contracts. -Preparation of the Curriculum and Syllabi creation. -Draft of Empirical Survey Tool creation. BEGINNING OF THE WORK ON THE INTELLECTUAL OUTPUT No1 (O1) – CURRICULUM (October 1, 2019 – November 1, 2020) | -Meetings with responsible officers in Tempus Foundation Serbia, University of Belgrade Rectorate. Meetings with University of Belgrade (BU) Faculty of Law Research Team. -Preparation of the Financial proposal for the 1st year of the project implementation (requested by the BU). -Creation of logo, memo, timesheet. Preparation of reports for the Beneficiary Space and Mobility Tool. -Visibility through creation of the webpage lawgem.ius.bg.ac.rs, leaflet -Securing English native speaking proof reading of all relevant LAWGEM documents. -Collecting the literature relevant for the LAWGEM Curriculum and syllabi creation. BEGINNING OF THE WORK ON THE INTELLECTUAL OUTPUT No 1 (O1) CURRICULUM. | -Meetings within Consortium members own team of researchers and completing the research teams. -Completing the partnership contracts per each consortium member. -Collecting the literature relevant for the LAWGEM Curriculum and syllabi creation. BEGINNING OF THE WORK ON THE INTELLECTUAL OUTPUT No 1 (O1) CURRICULUM Responsible partner University of Belgrade |
| November 2019 | Preparation of the documents and other material for the LAWGEM Kick-off meeting scheduled for Dec 12 and 13, 2019 BEGINNING OF THE WORK ON THE INTELLECTUAL OUTPUT No 2 (O2)– Empirical Survey Tool (November 1, 2019 –November 1, 2020) | - Kick-off meeting organization -Collecting the literature relevant for the LAWGEM Curriculum and syllabi creation. -Translation of the Grant Agreement and Annexes I, II, and IV into English. BEGINNING OF THE WORK ON THE INTELLECTUAL OUTPUT No 2 – Empirical Survey Tool. | -Collecting the literature relevant for the LAWGEM Curriculum and syllabi creation. -Work on the draft Empirical Survey Tool BEGINNING OF THE WORK ON THE INTELLECTUAL OUTPUT No 2 – Empirical Survey Tool Responsible partner University of Belgrade -Preparation of the draft of Empirical Survey Tool by the LAWGEM coordinator and all Consortium members` contact persons, as well as all other researchers. |
| December 2019 | Kick-off meeting December 12 and 13 | -Conducting the kick-off meeting. -Discussing Timetable of all activities, responsibilities. -Initiating the work on syllabi (gathering together researchers for particular courses). -Initiating the work on Empirical Survey Tool. | -Discussing timetables of all activities, responsibilities. -Starting the work on syllabi for particular courses by the researchers from all Consortium members. -Starting the collective work on Empirical Survey Tool, discussion, commenting, correcting the draft before the meeting (by email communication), and face to face during the Kick-off meeting. |
| REPORT to National Agency /Tempus Foundation (NA) after completing the Kick-Off Meeting (Dec 12 and 13, 2019) | Type of the Report | Deadline for submission of the reports by the coordinator to the NA | Deadline for submission of the reports by the partner contact persons to the coordinator |
|  | Financial and narrative report to NA | Dec 30, 2019 | Dec 25, 2019 |
| January 2020 | WORK on O1 and O2 | -Collecting the literature relevant for the LAWGEM Curriculum and syllabi creation. -Communication related to particular syllabi (email, skype communication). -Communication and exchange of ideas on the draft of Empirical Survey Tool (email, skype communication). | -Collecting the literature relevant for the LAWGEM Curriculum and syllabi creation. -Communication on the particular syllabi (email, skype communication). Communication and exchange of ideas on the draft of Empirical Survey Tool (email, skype communication). |
| February 2020 | WORK on O1 and O2 | -Communication on the particular syllabi (email, skype communication). -Communication and exchange of ideas on the draft of Empirical Survey Tool (email, skype communication). | -Communication on the particular syllabi (email, skype communication). Communication and exchange of ideas on the draft of Empirical Survey Tool (email, skype communication). |
| March 2020 | WORK on O1 and O2 | -Communication on the particular syllabi (email, skype communication). -Communication and exchange of ideas on the draft of Empirical Survey Tool (email, skype communication). | -Communication on the particular syllabi (email, skype communication). -Communication and exchange of ideas on the draft of Empirical Survey Tool (email, skype communication). |
| April 2020 | WORK on O1 (and O2 | -Communication on the particular syllabi, led by researchers from BU (email, skype communication). -Completing the Empirical Survey Tool and announcing it at the lawgem webpage | -Communication on the particular syllabi, led by researchers from BU (email, skype communication). -Completing the Empirical Survey Tool. -Final agreements regarding the Empirical Survey Tool online announcment. |
|  | Reports shall be submitted by the beneficiary/contact persons to the coordinator | First reporting period: | -Deadline for submission of the partnership reports by the beneficiary to the coordinator |
|  |  | From 1/10/2019 to 31/3/2020 | 15/4/2020 |
| May 2020 | WORK on O1 and O2 | -Communication on the particular syllabi (email, skype communication). -Agreement on the empirical survey sample and on the online conducting the survey at each partner university. | -Communication on the particular syllabi (email, skype communication). -Agreement on the empirical survey sample and on the online conducting the survey at each partner university |
| LTT, May 13-15, 2020 | Learning, Teaching, Training Workshop (LTT) for creating all syllabi and the Curriculum | -LAWGEM coordinator together with other Consortium members` contact persons will organize the whole activity and productive participation from all partner universities. All particular syllabi drafts will be completed during this workshop, and later on will be finalized through skype and email communication of the groups of researchers devoted to particular courses. | Responsible partner – University of Belgrade |
| REPORT to NA after completing LTT Workshop | Type of the Report | Deadline for submission of the reports by the coordinator to the NA | Deadline for submission of the reports by the beneficiary/contact persons to the coordinator |
|  | Financial and narrative report to NA | June 5, 2020 | May 25, 2020 |
| June 2020 | WORK on O1 and O2 | -Communication on the particular syllabi (email, skype communication). -Coordination of each partner universities Experts` analysis of the collected data. -The common methodology guidelines prepared for analysing the collected data. | -Communication on the particular syllabi (email, skype communication). Each partner university analyse the own collected data. The Consortium experts`, team led by BU experts, completes the comparative analysis. |
| July 2020 | WORK on O1 and O2 | -Completing the particular syllabi and the Curriculum (email, skype communication). -Coordination of each partner universities Experts` analysis of the collected data and of the use of the common methodology guidelines. | -Completing the particular syllabi and the Curriculum (email, skype communication). -Preparation of the experts` empirical survey reports announced by each and all partner universities. |
| August 2020 | WORK on O1 and O2 | -Announcing all particular survey analysis reports at the LAWGEM webpage. -Announcing the Curriculum and Syllabi. -Preparation of the BU experts` comparative analysis report. | -Final agreements concerning Curriculum and Syllabi (email, skype communication). -Final agreements regarding the Empirical Survey Tool dissemination and announcing of the final report based on a comparative analysis. |
| PARTNERSHIP REPORTING | Reports shall be submitted by the beneficiary to the coordinator | Second reporting period: | Deadline for submission of the partnership reports by the beneficiary to the coordinator |
|  |  | 1/4/2020 – 31/7/2020 | 15/8/2020 |
| September 2020 | WORK on O1 and O2 | -Communication on the particular syllabi, led by researchers from BU (email, skype communication). Coordination of the comparative analysis report discussion among partner universities. | -Communication on the particular syllabi, led by researchers from BU (email, skype communication). The comparative analysis report discussion among partner universities. |
| October 2020 | WORK on O1 and O2 | -Completing all syllabi and Curriculum. -Completing the common empirical survey report and preparation for announcing it at the LAWGEM webpage. | -Completing all syllabi and Curriculum. -Completing the common empirical survey report and preparation for announcing it at the LAWGEM webpage. |
| November 2020 | Transnational Project Meeting No 2 (TPM 2) and multiplier event No 1 (ME1) – Saarland Nov 18 to 20, 2020 | -Consortium members` contact persons coordinate the TPM 2 and ME1 organization together with the Saarland University contact person and the LAWGEM coordinator. -Presentation of particular syllabi by responsible members of all research teams. | Responsible partner – Saarland University -Organization of the TPM 2 and ME1, communication with Consortium members` contact persons and with the LAWGEM coordinator regarding all organizational and substantial issues. |
| REPORT to NA after holding TPM 2 and ME1 (Nov 18 to 20, 2020) | Type of the Report | Deadline for submission of the reports by the coordinator to the NA | Deadline for submission of the reports by the beneficiary to the coordinator |
|  | Financial and narrative report to NA | Dec 10, 2019 | Nov 30, 2019 |
|  | COMPLETING THE INTELLECTUAL OUTPUT No 1 (O1) CURRICULUM (Nov 1, 2020) COMPLETING THE INTELLECTUAL OUTPUT No 2 (O2) EMPIRICAL SURVEY TOOL (EST) (Nov 1, 2020) BEGINNING OF THE WORK ON THE INTELLECTUAL OUTPUT No 4 (O4) – Textbook Duration November 2020 – December 2021 | COMPLETING THE INTELLECTUAL OUTPUT No 1 (O1) CURRICULUM – COMPLETING THE INTELLECTUAL OUTPUT No 2 (O2) EMPIRICAL SURVEY TOOL (EST) - BEGINNING OF THE WORK ON THE INTELLECTUAL OUTPUT No 4 (O4)– Textbook | COMPLETING THE INTELLECTUAL OUTPUT No 1 (O1) CURRICULUM COMPLETING THE INTELLECTUAL OUTPUT No 2 (O2) EMPIRICAL SURVEY TOOL (EST) BEGINNING OF THE WORK ON THE INTELLECTUAL OUTPUT No 4 (O4)– Textbook Responsible partner University of Saarland |
| REPORT to NA after completing O 1 (Nov 2020) | Type of the Report | Deadline for submission of the reports by the coordinator to the NA | Deadline for submission of the reports by the beneficiary to the coordinator |
|  | Financial and narrative report to NA | Nov 20, 2020 | Nov 10, 2020 |
| REPORT to NA after completing O2 (Nov 2020) | Type of the Report | Deadline for submission of the reports by the coordinator to the NA | Deadline for submission of the reports by the beneficiary to the coordinator |
|  | Financial and narrative report to NA | Nov 20, 2020 | Nov 10, 2020 |
| December 2020 | -Preparation for starting up the accreditation procedure at each partner university (except Saarland University). -Promotion of the completed intellectual outputs - Curriculum and Empirical Survey Tool at the webpage and in the public media and social networks. | -Preparation for starting up the accreditation procedure at each partner university (except Saarland University) - Orebro, Lumsa, Cadiz, Belgrade University. -Promotion of the completed intellectual outputs -Curriculum and Empirical Survey Tool at the webpage and in the public media and social networks. | -Saarland University announces the call for chapters for the Textbook. -Saarland University proposes the ways of the communication regarding the Textbook preparation. -Saarland University starts procedures for introducing into the existent Curriculum the particular LAWGEM courses. |
| PARTNERSHIP REPORTING | Reports shall be submitted by the beneficiary to the coordinator | Third reporting period: | Deadline for submission of the partnership reports by the beneficiary to the coordinator |
|  |  | 1/8/2020 – 30/11/2020 | 15/12/2020 |
| January 2021 | Preparation for starting up the accreditation procedure at each partner university (except Saarland University). BEGINNING OF THE WORK ON THE INTELLECTUAL OUTPUT No 3 – Life Long Learning Platform (LLLP) (January 10, 2021 – August 31, 2022). BEGINNING OF THE WORK ON THE INTELLECTUAL OUTPUT Gender Equality Legal Clinic (GELC) – (January 10, 2021 – January 10, 2022. | Preparation for starting up the accreditation procedure at each partner university (except Saarland University) - Orebro, Lumsa, Cadiz, Belgrade University. BEGINNING OF THE WORK ON THE INTELLECTUAL OUTPUT No 3 – Life Long Learning Platform (LLLP) Responsible partner University of Belgrade BEGINNING OF THE WORK ON THE INTELLECTUAL OUTPUT Gender Equality Legal Clinic (GELC) | BEGINNING OF THE WORK ON THE INTELLECTUAL OUTPUT No 3 – Life Long Learning Platform (LLLP) BEGINNING OF THE WORK ON THE INTELLECTUAL OUTPUT Gender Equality Legal Clinic (GELC) Responsible partner University of Orebro |
| February 2021 | -Filling the accreditation forms. -Syllabus creation for GELC. -Constructing and constant enriching the LLLP on the basis of the already existent LAWGEM webpage. -Promotion and dissemination of Empirical Survey Tool, of the Curriculum at LLLP. -Preparation of the LLLP online pilot implementation of the master program Law and Gender. | -Filling the accreditation forms. -Syllabus creation for GELC. -Constructing and constant enriching the LLLP on the basis of the already existent LAWGEM webpage. -Promotion and dissemination of Empirical Survey Tool and the Curriculum. | -Filling the accreditation forms. -Syllabus creation for GELC by Orebro university, and initiating the communication with experts for legal clinic from other partner universities (skype, email communication). -Constructing and constant enriching the LLLP. -Planning the GELC promotion and dissemination at LLLP on the basis of the already existent LAWGEM webpage. -Promotion and dissemination of the Empirical Survey Tool and the Curriculum. -Collecting of the Textbook chapters. |
|  | TPM 3 and ME 2, February 4 and 5, 2021, Cadiz University | -Consortium members` contact persons coordinate the TPM 3 and ME 2 organization together with the Cadiz University contact person and the LAWGEM coordinator. -Presentation of particular syllabi by responsible members of all research teams. | Responsible partner - Cadiz University -Cadiz University contact person coordinates organization and activities regarding TPM 3 and ME2 with contact persons from other Consortium members` universities and with the LAWGEM coordinator. |
| PARTNERSHIP REPORTING | Reports shall be submitted by the beneficiary to the coordinator | Fourth reporting period: | Deadline for submission of the partnership reports by the beneficiary to the coordinator |
|  |  | 1/12/2020-15/2/2021 | 28/2/2021 |
| REPORT to NA after completing TPM3 and ME 2, February 3-5, 2021, Cadiz University | Type of the Report | Deadline for submission of the reports by the coordinator to the NA | Deadline for submission of the reports by the beneficiary to the coordinator |
|  | Financial and narrative report to NA | February 25, 2021 | February 15, 2021 |
| March 2021 | -Constructing and constant enriching the LLLP. -Promotion and dissemination of Empirical Survey Tool, of the Curriculum at LLLP. | -Constructing and constant enriching the LLLP. -Contact persons make plans how to enrich, promote, disseminate completed intellectual outputs and events. | -Constructing and constant enriching the LLLP. -Contact persons make plans how to enrich, promote, disseminate completed intellectual outputs and events. Collecting the Textbook chapters. |
| THE PROGRESS REPORT TO NA ON THE IMPLEMENTATION OF THE PROJECT |  | (at the latest) half-way period through the eligibility period, on 15/03/2021 | At the latest ten days before 28/02/2021 |
| April 2021 | -Constructing and constant enriching of the LLLP. Promotion and dissemination of Empirical Survey Tool, of the Curriculum at LLLP. -Preparation of the LLLP online pilot implementation of the master program Law and Gender (rulebook creation, online call for enrollment, moodle and online instruments preparation). | -Constructing and constant enriching of the LLLP. -Promotion and dissemination of Empirical Survey Tool, of the Curriculum at LLLP. -Preparation of the LLLP online pilot implementation of the master program Law and Gender (rulebook creation, online call for enrollment, moodle and online instruments preparation). | -Constructing and constant enriching of the LLLP. -Promotion and dissemination of Empirical Survey Tool, of the Curriculum at LLLP. -Preparation of the LLLP online pilot implementation of the master program Law and Gender (rulebook creation, online call for enrollment, moodle and online instruments preparation). -Collecting the Textbook chapters by the Saarland University responsible team. |
| May 2021 | -Constructing and constant enriching of the LLLP. -Promotion and dissemination of Empirical Survey Tool, of the Curriculum at LLLP. -Preparation of the LLLP online pilot implementation of the master program Law and Gender (rulebook creation, online call for enrollment, moodle and online instruments preparation). | -Constructing and constant enriching of the LLLP. Promotion and dissemination of Empirical Survey Tool, of the Curriculum at LLLP. -Preparation of the LLLP online pilot implementation of the master program Law and Gender (rulebook creation, online call for enrollment, moodle and online instruments preparation). -Discussing of the submitted articles. -Saarland experts` team in an agreement with other contact persons gives particular chapter to the intenal LAWGEM reviewers as well as to external. | -Constructing and constant enriching of the LLLP. -Promotion and dissemination of Empirical Survey Tool, of the Curriculum at LLLP. -Preparation of the LLLP online pilot implementation of the master program Law and Gender ((rulebook creation, online call for enrollment, moodle and online instruments preparation). -Discussing of the submitted articles. -Saarland experts` team gives particular chapter to the intenal LAWGEM reviewers as well as to external. |
| June 2021 | Deadline for the Textbook articles writing. | Deadline for the Textbook articles writing. | Deadline for the Textbook articles writing. |
| July 2021 | Textbook articles reviewing | Textbook articles reviewing and correcting. | Textbook articles reviewing and correcting. |
| PARTNERSHIP REPORTING | Reports shall be submitted by the beneficiary to the coordinator | Fifth reporting period | Deadline for submission of the partnership reports by the beneficiary to the coordinator |
|  |  | 16/2/2021 – 30/6/2021 | 15/7/2021 |
| August 2021 | Call for LAWGEM pilot online enrollment. Proof-reading of the Textbook articles. Activating the GELC online in all consortium members. | Call for LAWGEM pilot online enrollment. Proof-reading of the Textbook articles. Activating the GELC online in all consortium members. | Call for LAWGEM pilot online enrollment. Proof-reading of the Textbook articles. Activating the GELC online in all consortium members. |
| September 2021 | -Intensive promotion of the online pilot master Law and Gender. -Activating the GELC online in all consortium members. | -Intensive promotion of the Law and gender online pilot master Law and Gender. -Activating the GELC online in all consortium members. -Promotion of the LAWGEM intellectual outputs and events in the public media and social networks. | -Intensive promotion of the Law and gender online pilot master Law and Gender. -Activating the GELC online in all consortium members. -Promotion of the LAWGEM intellectual outputs and events in the public media and social networks. |
| October 2021 | -Intensive promotion of the online pilot master Law and Gender. -Activating the GELC online in all consortium members. -Implementing online master Law and Gender. -Promoting online master Law and Gender. | -Intensive promotion of the online pilot master Law and Gender. -Activating the GELC online in all consortium members. -Promotion of the LAWGEM intellectual outputs and events in the public media and social networks. -Publishing of the textbook. -Implementing online master Law and Gender. -Promoting online master Law and Gender. | -Intensive promotion of the online pilot master Law and Gender. -Activating the GELC online in all consortium members. -Promotion of the LAWGEM intellectual outputs and events in the public media and social networks. -Publishing of the textbook. -Implementing online master Law and Gender. -Promoting online master Law and Gender. |
|  | TPM 4 and ME 3, Orebro University, October 6-8, 2021 | All consortium members take part - together with Orebro University contact person and the LAWGEM coordinator in organizing the TPM 4 and ME3. For ME3, all consortium members secure the participation of a few members from each research team in order to take part in presenting: GELC, LLLP, and particular syllabi. | Responsible partner - Orebro University -Orebro University contact person coordinates activities and communicates all relevant issue related to TPM 4 and ME3 with the contact persons from other Consortium members and with the LAWGEM coordinator. At ME3 - Presentation of GELC, presentation of LLLP, and presentation of particular syllabi. |
| REPORT to NA after completing TPM 4 and ME 3 - October 6-8, 2021, Orebro University | Type of the Report | Deadline for submission of the reports by the coordinator to the NA | Deadline for submission of the reports by the beneficiary to the coordinator |
|  | Financial and Narrative Report to NA | November 5, 2021 | October 22, 2021 |
| November 2021 | -Publishing of the Textbook. | -Support of all Consortium members and the LAWGEM coordinator to the representatives of Saarland University regarding the ublishing of the Textbook. | -Publishing of the Textbook by the german publisher and under responsibility of Saarland contact person, and the LAWGEM coordinator and other Consortium members contact persons . |
| PARTNERSHIP REPORTING | Reports shall be submitted by the beneficiary to the coordinator | Sixth reporting period: | Deadline for submission of the partnership reports by the beneficiary to the coordinator |
|  |  | 1/7/2021 – 31/10/2021 | 15/11/2021 |
| December 2021 | COMPLETING OF THE WORK ON THE INTELLECTUAL OUTPUT No 4 (O4) – Textbook (duration November 2020 – December 2021) | COMPLETING OF THE WORK ON THE INTELLECTUAL OUTPUT No 4 (O4) – Textbook | COMPLETING OF THE WORK ON THE INTELLECTUAL OUTPUT No 4 (O4) – Textbook Responsible partner University of Saarland |
| REPORT to NA after completing the O 4 - Textbook | Type of the Report | Deadline for submission of the reports by the coordinator to the NA | Deadline for submission of the reports by the beneficiary to the coordinator |
|  | Financial and narrative report to NA | Jan 20, 2022 | Jan 10, 2022 |
| January 2022 | COMPLETING OF THE WORK ON THE INTELLECTUAL OUTPUT No 5 Gender Equality Legal Clinic (GELC) – (January 1, 2021 – January 10, 2022) | COMPLETING OF THE WORK ON THE INTELLECTUAL OUTPUT No 5 Gender Equality Legal Clinic (GELC) | COMPLETING OF THE WORK ON THE INTELLECTUAL OUTPUT No 5 Gender Equality Legal Clinic (GELC) Responsible partner University of Orebro |
| January 2022 | TPM 5 and ME 4, January 19-21, 2022, Belgrade | -All consortium members take part - together with Belgrade University contact person and all consortium members contact persons in organizing the TPM 4 and ME3. -For ME3, all consortium members secure the participation of a few members from each research team in order to take part in presenting particular syllabi as well as in initial analysis of all intellectual outputs: Curriculum, LLLP, GELC, and Empirical Survey Tool. | LAWGEM coordinator - together with other contact persons from all Consortium members - organizes TPM5 and ME 4. -For ME3, University of Belgrade and all consortium members secure the participation of a few members from each research team in order to take part in presenting particular syllabi as well as in initial analysis of all intellectual outputs: Curriculum, LLLP, GELC, and Empirical Survey Tool. |
| REPORT to NA after completing TPM 5 and ME 4, January 19-21, 2022, Belgrade | Type of the Report | Deadline for submission of the reports by the coordinator to the NA | Deadline for submission of the reports by the beneficiary to the coordinator |
|  | Financial and narrative report to NA | February 10, 2022 | January 30, 2022 |
| REPORT to NA after completing O 5 – GELC (Jan 10, 2022) | Type of the Report | Deadline for submission of the reports by the coordinator to the NA | Deadline for submission of the reports by the beneficiary to the coordinator |
|  | Financial and narrative report to NA | Feb 01, 2022 | Jan 20, 2022 |
| February 2022 | -GELC completed and online announced. -Promotion of GELC, Textbook, Empirical survey Tool and the Curriculum, e.g. online pilot master programme Law and Gender. -Promotion of an online master LAW AND GENDER. | -Promotion of GELC, Textbook, Empirical Survey Tool and the Curriculum, e.g. online pilot master programme Law and Gender on LLLP and in public media and social networks, as well as on academic events inside the LAWGEM project and outside it. -Promotion of an online master LAW AND GENDER. | -Promotion of GELC, Textbook, Empirical Survey Tool and the Curriculum, e.g. online pilot master programme Law and Gender on LLLP and in public media and social networks, as well as on academic events inside the LAWGEM project and outside it. -Promotion of an online master LAW AND GENDER. |
| March 2022 | -Promotion of GELC, Textbook, Empirical survey Tool and the Curriculum, e.g. online pilot master programme Law and Gender. -Promotion of an online master LAW AND GENDER,including the GELC. -Public promotion of the Textbook in media and academic events. | -Promotion of GELC, Textbook, Empirical survey Tool and the Curriculum, e.g. online pilot master programme Law and Gender. -Promotion of an online master LAW AND GENDER, including the GELC Public promotion of the Textbook in media and academic events. | -Promotion of GELC, Textbook, Empirical survey Tool and the Curriculum, e.g. online pilot master programme Law and Gender. -Promotion of an online master LAW AND GENDER, including the GELC. Public promotion of the Textbook in media and academic events. |
| PARTNERSHIP REPORTING | Reports shall be submitted by the beneficiary to the coordinator | Seventh reporting period: | Deadline for submission of the partnership reports by the beneficiary to the coordinator |
|  |  | 1/11/2021 – 28/2/2022 | 15/3/2022 |
| April 2022 | -Promotion of GELC, Textbook, Empirical Survey Tool and the Curriculum, e.g. online pilot master programme Law and Gender on LLLP and in public media and social networks, as well as on academic events inside the LAWGEM project and outside it. | -Promotion of GELC, Textbook, Empirical Survey Tool and the Curriculum, e.g. online pilot master programme Law and Gender on LLLP and in public media and social networks, as well as on academic events inside the LAWGEM project and outside it. | -Promotion of GELC, Textbook, Empirical Survey Tool and the Curriculum, e.g. online pilot master programme Law and Gender on LLLP and in public media and social networks, as well as on academic events inside the LAWGEM project and outside it. |
| May 2022 | -Promotion of GELC, Textbook, Empirical Survey Tool and the Curriculum, e.g. online pilot master programme Law and Gender on LLLP and in public media and social networks, as well as on academic events inside the LAWGEM project and outside it. | -Promotion of GELC, Textbook, Empirical Survey Tool and the Curriculum, e.g. online pilot master programme Law and Gender on LLLP and in public media and social networks, as well as on academic events inside the LAWGEM project and outside it. | -Promotion of GELC, Textbook, Empirical Survey Tool and the Curriculum, e.g. online pilot master programme Law and Gender on LLLP and in public media and social networks, as well as on academic events inside the LAWGEM project and outside it. |
| May 2022 | ME 5, May 10-11, 2022, LUMSA Palermo | -All consortium members take part - together with LUMSA University contact person in organizing the TPM 4 and ME3. -For ME5, all consortium members secure the participation of a few members from each research team in order to take part in presenting particular syllabi as well as in initial analysis of all intellectual outputs: Curriculum, LLLP, GELC, and Empirical Survey Tool. -Analysis of the Law and Gender master study programme sustainability. -Analysis of the accreditation results. -Discussing the common applying for the Erazmus Mundus Joint Master Program. | Lumsa University contact person takes responsibility for organizing this concluding multiplier event, a nd does it in a coordination with all consortium members contact persons and the LAWGEM coordinator. At ME5 will be conducted analysis of all intellectual outputs - Curriculum, LLLP, GELC, Empirical Survey Tool, Textbook. Also, the Law and Gender master study programme sustainability will be taken into consideration. Lumsa University contact person will organize with the LAWGEM coordinator a special concluding discussion on the accreditation results, as well as on the common applying for the Erazmus Mundus Joint Master Program. |
| REPORT to NA after completing ME 5, May 10-11, 2022, LUMSA Palermo | Type of the Report | Deadline for submission of the reports by the coordinator to the NA | Deadline for submission of the reports by the beneficiary to the coordinator |
|  | Financial and narrative report to NA | June 5, 2022 | May 25, 2022 |
| June 2022 | -Completing the pilot online Law and Gender master programme. -Analysis of the accreditation results. -Discussing the common applying for the Erazmus Mundus Joint Master Program. | -Completing the pilot online Law and Gender master programme. -Announcing the master implementation results at LLLP, and in public media and social media. -Analysis of the accreditation results. -Discussing the common applying for the Erazmus Mundus Joint Master Program. | -Completing the pilot online Law and Gender master programme. -Announcing the master implementation results at LLLP, and in public media and social media. -Analysis of the accreditation results. -Discussing the common applying for the Erazmus Mundus Joint Master Program. |
| PARTNERSHIP REPORTING | Reports shall be submitted by the beneficiary to the coordinator | Eighth reporting period: | Deadline for submission of the partnership reports by the beneficiary to the coordinator |
|  |  | 1/3/2022 - 31/5/2022 | 15/6/2022 |
| July 2022 | -Public promotion of the Textbook, GELC, master Law and Gender, Empirical Survey Tool. -Promotion of all intellectual outputs and events on LLLP. -Discussion on the Follow up, and sustainability of LAWGEM results. -Analysis of the accreditation results. -Discussing the common applying for the Erazmus Mundus Joint Master Program. | -Public promotion of the Textbook, GELC, master Law and Gender, Empirical Survey Tool. -Promotion of all intellectual outputs and events on LLLP. -Discussion on the Follow up, and sustainability of LAWGEM results. -Analysis of the accreditation results. -Discussing the common applying for the Erazmus Mundus Joint Master Program. | -Public promotion of the Textbook, GELC, master Law and Gender, Empirical Survey Tool. -Promotion of all intellectual outputs and events on LLLP. -Discussion on the Follow up, and sustainability of LAWGEM results. -Analysis of the accreditation results. -Discussing the common applying for the Erazmus Mundus Joint Master Program. |
| August 2022 | COMPLETING OF THE WORK ON THE INTELLECTUAL OUTPUT No 3 Lifelong Learning Platform (LLP). Duration January 2022 – August 2022) | COMPLETING OF THE WORK ON THE INTELLECTUAL OUTPUT No 3– Lifelong Learning Platform (LLP) | COMPLETING OF THE WORK ON THE INTELLECTUAL OUTPUT No No 3– Lifelong Learning Platform (LLP). Responsible partner University of Belgrade |
| REPORT to NA after completing O 3 - LLLP (Aug 31, 2022) | Type of the Report Financial and narrative report to NA | Deadline for submission of the reports by the coordinator to the NA | Deadline for submission of the reports by the beneficiary to the coordinator |
|  |  | Sept 20, 2022 | Sept 10, 2022 |
| PARTNERSHIP REPORTING | Reports shall be submitted by the beneficiary to the coordinator | Ninth reporting period: | Deadline for submission of the partnership reports by the beneficiary to the coordinator |
|  |  | 1/6/2022-31/8/2022 | 30/9/2022 |
| September 2022 | -Promotion of all intellectual outputs and events. -Discussion on the Follow up, and sustainability of LAWGEM results. -Analysis of the accreditation results. -Discussing the common applying for the Erazmus Mundus Joint Master Program. | -Promotion of all intellectual outputs and events. -Discussion on the Follow up, and sustainability of LAWGEM results. -Analysis of the accreditation results. -Discussing the common applying for the Erazmus Mundus Joint Master Program. | -Promotion of all intellectual outputs and events. -Discussion on the Follow up, and sustainability of LAWGEM results. -Analysis of the accreditation results. -Discussing the common applying for the Erazmus Mundus Joint Master Program. |
| October 2022 | FINAL REPORT to NA | 31/10/2022 | 30.09/2022 |